## Mom1(1_2_17)
Minutes of Meeting (1st Febuary 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-02-01 | Discussing about "Smart Drawer" | 2:30 pm to 3:00 | Jain Krisha , Patel Dhyan, Pansuria Zarna | Defination OF the Project | Disscusion about project defination.Scope of the Project.
|  |  |  | Hardware Requirement | Disscusion about hardware product which are needed for development
|  |  |  | Technology Uses | IOT technology… Current Application of IOT.
|  |  |  | Cost Estimation and view Rfid Tag | Cost of the rfid tag. Rfid Reader cost.
|  |  |  | Scope Of The Project | Add other functionality like prevent For stolen of goods. Transaction of the goods. Availibale stock in inventory.

## Mom2(6_2_17)
Minutes of Meeting (6th February 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-01-06 | Discussing about "Smart Drawer" | 2:30 pm to 2:45 | Patel Dhyan,Pansuriya Zarna | Rfid Tag | Available Rfid Tag Contains default unique keys.

## Mom3(20_2_17)
Minutes of Meeting (20th FEB 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-02-20 | Discussing about "Smart Drawer" | 5:15 pm to 6:00 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | DataBase | Disscusion about database its tables and entity
|  |  |  | Function Requirement | Disscusion about other more Function Requirement like transaction management,alert when item placed in wrong place
|  |  |  | Security of the System | Improve Security by providing Authenticated person with drawer.Add tag to Reader to prevent steal of reader
|  |  |  | Rfid tag | 1.Which types of tag is used. 2.Pricing of the tags. 3.memory of tag .
|  |  |  | Rfid Reader | 1.Available Rfid Reader. 2.Frequency of Reader.
|  |  |  | Connection between Rfid Reader | Connection of RFID Reader with Each Of Other.

## Mom4(21_2_17)
Minutes of Meeting (21st Feb 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-02-21 | Discussing about "Smart Drawer" | 2:30 to 2:45 and 5:00 to 5:30 | Jain Krisha,Patel Dhyan,Pansuriya Zarna Kirti mam(Embedded) | Rfid Reader | Disscusion about what types of reader is needed.Range,feature of the reader. Rfid tag Reader Reads the tag and display in Notpad file.
*this meeting is with Saurabh sir and Shri Ma'am.

## Mom5(4_3_17)
Minutes of Meeting (4th March 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-03-04 | Discussing about "Smart Drawer" | 6:00 pm to 6:30 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | Web Serviece using marven | Disscusion about Web Serviece.Finding Framwork for making user friendly and convinient url | Dhyan Patel,Pansuria Zarna,krisha jain |  |  | running

## Mom6(7_3_17)
Minutes of Meeting (7th March 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-03-07 | Discussing about "Smart Drawer" | 12:00 pm to 12:30 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | User Interface | Disscusion about User Friendly Interface what are the required fields. | Dhyan Patel,Pansuria Zarna,krisha jain |  |  | running

## Mom7(9_3_17)
Minutes of Meeting (09th MARCH 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-03-09 | Discussing about "Smart Drawer" | 12:00 pm to 12:30 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | User Interface | Disscusion about project management tool.Changes in ui make it dynamically. | Dhyan Patel,Pansuria Zarna,krisha jain |  |  | running

## Mom8(20_3_17)
Minutes of Meeting (20th MARCH 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-03-20 | Discussing about "Smart Drawer" | 12:00 pm to 12:30 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | User Interface | Approvement of the Forms with Designing,Styling and Validation. | Dhyan Patel,Pansuria Zarna,krisha jain |  |  | running
|  |  |  | Web Service | Give questions regarding web service.

## Mom9(29_3_17)
Minutes of Meeting (29th MARCH 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-03-29 | Discussing about "Smart Drawer" | 3:00 pm to 3:30 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | Error solving | Build Fail error solving.How it occures?How to solve it | Dhyan Patel,Pansuria Zarna,krisha jain |  |  | running
|  |  |  | REST Web Service | Discussion about Rest Web Service.Usages of It.Requirment of web Service.

## Mom10(7_4_17)
Minutes of Meeting (7th April 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-04-07 | Discussing about "Smart Drawer" | 11:00 am to 11:20 am | Jain Krisha , Patel Dhyan, Pansuria Zarna | Web Service | Approvment of Demo Web Service.All Request of web service verified. | Dhyan Patel, Pansuria Zarna |  |  | running

## Mom11(20_4_17)
Minutes of Meeting (20th April 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-04-20 | Discussing about "Smart Drawer" | 5:00 pm to 5:15 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | Web Service | Approvment of Demo Web Service according to project in working condition. | Jain Krisha , Patel Dhyan, Pansuria Zarna |  |  | running

## Mom12(12_5_17)
Minutes of Meeting (12th May 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-05-12 | Discussing about "Smart Drawer" | 4:15 pm to 4:45 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | Web Service | All Web service created according to project like person, item, tagbank,map person,map item | Dhyan Patel, Pansuria Zarna, Jain Krisha |  |  | running
|  |  |  | Integration | Discussion about Integration of web service with Database.

## Mom13(1_6_17)
Minutes of Meeting (1st June 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-06-01 | Discussing about "Smart Drawer" | 4:30 pm to 5:15pm | Patel Dhayan | Project Status | Current Project Status.Completed and remaining modules of project. Documentation of the project.Deadline of the Project. | Dhyan Patel, Pansuria Zarna, Jain Krisha |  |  | running

## Mom14(5_6_17)
Minutes of Meeting (5th June 2017)
Date | Agenda | Actual Duration | Attendees | Points Discussed | Details | Responsible Person | Target Date of completion | Actual Date of completion | Action Item Status | Remarks
2017-06-05 | Discussing about "Smart Drawer" | 6:45 pm to 6:55 pm | Jain Krisha , Patel Dhyan, Pansuria Zarna | Dynamic Integration | Dynamically integration of the web service and datbase.Display related Items after selecting drawer using ajax. | Dhyan Patel, Pansuria Zarna, Jain Krisha |  |  | running