## Project Plan
ID | Task Name | Start | Finish | Resourse | Status | Remark
1 | Problem Statement Understanding | 2017-02-02 | 2017-02-03 | Darshna Ma'am & Saurabh Sir | Completed
2 | What is RFID and how it's Working | 2017-02-03 | 2017-02-04 | Darshna Ma'am | Completed
3 | Feasiblituy Study of System | 2017-02-04 | 2017-02-06 |  | Completed | excluding Sunday 5th
4 | Project analysis | 2017-02-06 | 2017-02-07 | Saurabh sir | Completed
5 | Base Requirement Getharing | 2017-02-07 | 2017-02-08 | Saurabh sir | Completed
6 | Devide Systems in to Modules | 2017-02-09 | 2017-02-10 |  | Completed
7 | SRS making v1.0 | 2017-02-13 | 2017-02-15 |  | Completed
8 | SRS Review | 2017-02-15 | 2017-02-16 | Darshna Ma'am & Saurabh sir | Completed
9 | SRS modification as par Suggession | 2017-02-16 | 2017-02-17 |  | Completed
10 | Project Planing | 2017-02-17 | 2017-02-20 |  | Completed | excluding week ends 18th and 19th
11 | Database Design | 2017-02-20 | 2017-02-22 | Saurabh sir | Completed | It is tentitive, it might change based on the requirement
12 | Code of Diffrant modules | 2017-02-23 | 2017-03-17 | Darshna Ma'am & Saurabh sir | Completed
13 | Insert Peson (with it's deatis) in database | 2017-02-23 | 2017-03-02 |  | Completed | excluding weekends 24th,25th and 26th and it's tantative based on technoloy which we gona use like MVC/RestAPI/SOAP
14 | Insert Item (with it's deatis) in database | 2017-03-02 | 2017-03-04 |  | Completed | it's tantative based on technoloy which we gona use like MVC/RestAPI/SOAP
15 | Take Tags from file (Gateway) and map to the Person/Item | 2017-03-06 | 2017-03-08 | Saurabh sir | Completed | it's tantative based on technoloy which we gona use like MVC/RestAPI/SOAP
16 | Making GUI | 2017-02-27 | 2017-03-17 | Darshna Ma'am & Saurabh sir | Completed
17 | Demo WebService | 2017-03-28 | 2017-04-10 |  | Completed
18 | Smart Drawer Web Service with database | 2017-04-10 | 2017-05-12 | Saurabh sir | Completed
19 | Integration of the web service with GUI | 2017-05-15 | 2017-06-25 | Saurabh sir | Completed
20 | Integrate All modules | 2017-05-25 | 2017-06-05 | Darshna Ma'am & Saurabh sir | Completed
22 | Testing 1.0 | 2017-06-06 | 2017-06-06 |  | Completed
23 | Deploy System
24